## Sheet1
Values are Based on Importance: H - High, M - Medium, L - low
Estimated Time is measured in Days
Module | Feature Name | Value | Estimated Time | Elaspsed Time | Release
1.1 | Access to Server | H | 1 |  | 1
1.2 | Database Design | H | 5 |  | 1
1.3 | Input Form questions | M | 3 |  | 1
1.4 | Development Envrioments created | H | 2 |  | 1
1.5 | Version Control created and accessile | H | 2 |  | 1
2 | U.I design of layouts created | H | 14 |  | 1
2.1 | U.I design intergration | H | 14 |  | 1
2.2 | Homepage | H | 7 |  | 1
2.3 | Category page template | M | 7 |  | 1
2.4 | Graph Integration | H | 7 |  | 1
2.5 | Graphs display data from database correctly | H | 7 |  | 1
3.1 | Input forms for continual data gathering | M | 14 |  | 1
3.2 | Input forms correctly save data to database | M | 7 |  | 1
WATERLINE
4.1 | New database data is viewable to website | L | 14 |  | 2
4.2 | Modals for individual category graph displays | L | 14 |  | 2